## Project Gantt Chart
Phase Name | Task Name | Role Responsible | Start Date | End Date | Duration (Days) | 01-Feb | 02-Feb | 03-Feb | 04-Feb | 05-Feb | 06-Feb | 07-Feb | 08-Feb | 09-Feb | 10-Feb | 11-Feb | 12-Feb | 13-Feb | 14-Feb | 15-Feb | 16-Feb | 17-Feb | 18-Feb | 19-Feb | 20-Feb | 21-Feb | 22-Feb | 23-Feb | 24-Feb | 25-Feb | 26-Feb | 27-Feb | 28-Feb | 01-Mar | 02-Mar | 03-Mar | 04-Mar | 05-Mar | 06-Mar | 07-Mar | 08-Mar | 09-Mar | 10-Mar | 11-Mar | 12-Mar | 13-Mar | 14-Mar | 15-Mar | 16-Mar | 17-Mar | 18-Mar | 19-Mar | 20-Mar | 21-Mar | 22-Mar | 23-Mar | 24-Mar | 25-Mar | 26-Mar | 27-Mar | 28-Mar | 29-Mar | 30-Mar | 31-Mar
Project Initiation | Project kickoff meeting | TYN Executive | 2026-02-01 | 2026-02-03 | 2 | bar: 01-Feb to 03-Feb
Requirement Analysis | Requirement gathering | Backend Team | 2026-02-04 | 2026-02-10 | 6 | bar: 04-Feb to 10-Feb
BRD Finalization | Finalize BRD document | TYN Executive | 2026-02-11 | 2026-02-15 | 4 | bar: 11-Feb to 15-Feb
Architecture Design | System architecture design | Backend Team | 2026-02-12 | 2026-02-18 | 6 | bar: 12-Feb to 18-Feb
Database Design | PostgreSQL schema design | Database Team | 2026-02-16 | 2026-02-22 | 6 | bar: 16-Feb to 22-Feb
Backend Development | Auth module | Backend Team | 2026-02-20 | 2026-03-10 | 18 | bar: 20-Feb to 10-Mar
Frontend Development | Login UI | Frontend Team | 2026-02-25 | 2026-03-15 | 18 | bar: 25-Feb to 15-Mar
Azure Cloud Setup | Key vault setup | DevOps & Azure Team | 2026-03-01 | 2026-03-10 | 9 | bar: 01-Mar to 10-Mar
Integration | API integration | Backend Team | 2026-03-12 | 2026-03-20 | 8 | bar: 12-Mar to 20-Mar
Testing | Functional testing | Testing & QA Team | 2026-03-18 | 2026-03-24 | 6 | bar: 18-Mar to 24-Mar
Bug Fixing | Fix reported issues | Backend Team | 2026-03-22 | 2026-03-27 | 5 | bar: 22-Mar to 27-Mar
Final Deployment | Deploy to Azure | DevOps & Azure Team | 2026-03-28 | 2026-03-30 | 2 | bar: 28-Mar to 30-Mar
Documentation | Prepare project report | Student Module Team | 2026-03-20 | 2026-03-30 | 10 | bar: 20-Mar to 30-Mar
Final Submission | Submit project | TYN Executive | 2026-03-31 | 2026-03-31 | 1 | bar: 31-Mar